## Sheet1
Instructions: 1. Select one of the available status for each task. 2. If you decided on which of your teammate is going to work on a particular task, the status should be changed to "Assigned" and that student's name should be entered under "Assigned To". 3. After you start working on a task, change the status to "In Progress". Once it's completed, the status should be "Completed". If it can't be completed because of an issue, the staus should be "Blocked" and comment on why it's blocked. 4. Select expected start dates and end dates for every task. 5. Updated the actual start date and end date of your tasks regularly.
Task | Status | Assigned To | Exp. Start Date | Exp. End Date | Actual Start Date | Actual End Date | Comments
Analyze HTML | Completed | Darwin | 2018-04-17 | 2018-04-18 | 2018-04-17 | 2018-04-18 | Determine usefulness extension opportunities
Analyze PHP | Completed | Clayton | 2018-04-17 | 2018-04-18 | 2018-04-17 | 2018-04-18 | Determine usefulness
Arduino Sketch Code | Completed | Jacob | 2018-04-15 | 2018-04-18 | 2018-04-15 | 2018-04-18
Wire-up Arduino | Completed | Clayton | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | Potentially immediately blocked for code spec, sensor reordering, etc.
Testing | Completed | Jacob | 2018-05-01 | 2018-05-01
UI Design | Completed |  | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-05-01 | Using previous group UI design, augmenting with AI
AI Design | Completed | Clayton | 2018-04-19 | 2018-04-25 | 2018-04-19 | 2018-05-01 | Average forecast
Poster
Collect Data | Completed | All | 2018-04-24 | 2018-04-26 | 2018-04-25 | 2018-04-26 | Done by Transportation Services
Database Push C Code | Completed | Jacob | 2018-04-19 | 2018-04-27 | 2018-04-24 | 2018-04-27 | Using cURL through POST on a webpage
Massage PHP for New Table | Completed | Darwin | 2018-04-19 | 2018-04-22 | 2018-04-19 | 2018-04-22
Impovements Document | Completed | All | 2018-04-28 | 2018-05-01 | 2018-04-29 | 2018-05-01
Arduino API | Completed | Jacob | 2018-05-01 | 2018-05-01 | 2018-05-01 | 2018-05-01
DB API | Completed | Jacob | 2018-05-01 | 2018-05-01 | 2018-05-01 | 2018-05-02
PHP API | Completed | Darwin | 2018-04-29 | 2018-05-02 | 2018-04-29 | 2018-05-02